SECOND INNINGS

90-Day Validation & Execution Plan

1 October - 31 December 2026

Working Document for Deepak Sogani & Aman Pratap Singh

CONFIDENTIAL | WORKING DRAFT

# 1. Purpose

The next 90 days are a validation phase. The objective is to start small, work with real young people, learn from actual usage, test referrals and willingness to pay, and use evidence to decide the direction for 2027.

Core question: Can Second Innings create enough value for young people that they act on the conversation, return when useful, refer others, and eventually pay for structured mentoring?

# 2. Working Principle for Aman's Association

Aman's academics will remain his first priority. His role during this validation phase will primarily be to help design, set up and progressively improve a simple and reliable technical system - not to manage the daily operations of Second Innings.

During the initial setup phase, particularly while he is on vacation, Aman may devote time according to his interest, availability and what he considers technically necessary to establish the first working system.

Once his regular academic schedule resumes, Deepak will own the routine student-facing and operational activities. Aman will remain involved in technical development, review and evolution at mutually convenient milestones.

The intention is not merely to seek Aman's support for the initial technical setup, but to keep him meaningfully associated with the journey as Second Innings evolves, while ensuring that this association complements rather than competes with his academic journey.

# 3. Role Clarity

| Area | Deepak | Aman |
| --- | --- | --- |
| Mentoring conversations | Owns | No routine role |
| Student outreach & invitations | Owns | No routine role |
| 7-day follow-ups | Owns | No routine role |
| Opportunity research / Knowledge Bank | Owns | Technical support only if needed |
| Student records & content | Owns content/usage | Helps establish structure |
| Technology selection | Provides requirements | Leads initially |
| Initial technical setup | Learns & tests | Sets up / guides |
| Routine system operation | Owns | No routine role |
| Technical troubleshooting | First-level use | Supports when required |
| Technology improvements | Provides usage feedback | Advises / builds when justified |
| Analytics / dashboard | Uses & reviews | Helps establish |
| Paid offering | Owns service & pricing decision | Technical support if required |
| 2027 direction | Joint discussion | Joint discussion |

# 4. Master Execution Calendar

| Date / Period | Task | Responsible | Expected Output |
| --- | --- | --- | --- |
| 30 Sep | Working meeting: freeze October execution plan | Both | Must Have Now / Can Wait / Not Needed list |
| 30 Sep | Decide simplest technology stack | Aman leads + Deepak | Tools for presence, intake, booking, records and follow-up |
| 1 Oct | Prepare concise Second Innings introduction | Deepak | Final introductory copy |
| 1 Oct | Prepare student intake questions | Deepak | Short intake content |
| 1 Oct | Prepare post-session note format | Deepak | Standard mentoring record |
| 1-3 Oct | Set up basic enquiry / intake mechanism | Aman | Working student entry process |
| 1-3 Oct | Set up booking / calendar mechanism | Aman | Simple slot-request / booking process |
| 1-3 Oct | Set up student record & follow-up system | Both | Usable tracker / database |
| 2-4 Oct | Deepak learns routine operation of systems | Both | Deepak can operate basic system independently |
| 3-4 Oct | Test complete student journey | Both | Friction points identified and corrected |
| 4-5 Oct | Prepare first list of approx. 20 participants | Deepak | A/B/C participant groups |
| 5-7 Oct | Conduct 3-5 pilot conversations | Deepak | First process observations |
| 7 Oct | Quick review after pilots | Both | Only essential corrections |
| 8-14 Oct | Soft launch / first invitations | Deepak | Approx. 5 completed conversations |
| After every session | Complete session notes | Deepak | Clean mentoring record |
| 7 days after session | Follow up on agreed action | Deepak | Action status / learning |
| Every Friday | Review themes and learning | Deepak | Weekly Founder Learning Note |
| 15-31 Oct | Build first cohort | Deepak | Approx. 15-20 students cumulatively |
| 31 Oct | Month-1 review | Both | What worked / failed / needs change |
| 1-15 Nov | Seek suitable referrals | Deepak | New participants beyond existing relationships |
| 1-15 Nov | Mentor referred participants | Deepak | 5-8 conversations with people less familiar with Deepak |
| 15 Nov | Progress review | Both | Referral and process observations |
| 16-25 Nov | Analyse recurring needs / repeat behaviour | Deepak | What students actually seek |
| 25-30 Nov | Technology review based on usage | Both | V2 changes only if justified |
| 25-30 Nov | Define simple December paid format | Deepak; Aman input if needed | Clear offer and operating process |
| 1-15 Dec | Test paid format with new participants | Deepak | First willingness-to-pay evidence |
| 1-15 Dec | Ensure payment / confirmation process works | Aman if required | Smooth technical process |
| 15 Dec | Mid-month review | Both | Early paid-validation findings |
| 16-28 Dec | Continue cases and collect evidence | Deepak | Final validation data |
| 29-31 Dec | 90-day review | Both | Evidence-based 2027 direction |

# 5. Month-wise Validation Plan

## October - Build, Test and Work with the First Cohort

1-7 Oct: Build and test only the minimum operating system.

8-14 Oct: Soft launch and complete approximately five conversations.

15-31 Oct: Build towards approximately 15-20 students cumulatively, with proper notes and 7-day follow-up.

October objective: Work meaningfully with approximately 15-20 young people while testing the complete mentoring and follow-up process. The number is a direction, not a quota.

## November - Test Whether the Model Travels

Ask only students who genuinely experienced value to refer one young person who may benefit.

Aim for 5-8 conversations with young people who did not previously have a meaningful relationship with Deepak.

Study why people come, what they return for, what they refer others for and what actions they actually take.

November objective: Test whether the value of Second Innings can travel beyond Deepak's existing relationships.

## December - Test Willingness to Pay

Use October-November learning to define a simple paid format for new participants.

Do not retrospectively change the understanding for participants who entered the validation phase as free participants.

Measure willingness to pay rather than trying to maximise revenue.

December objective: Generate the first evidence that a young person or parent without a pre-existing relationship sees enough value to pay for a structured mentoring engagement.

# 6. Minimum Student Journey to Be Enabled

Hear / Learn about Second Innings  ->  Contact / Enquire  ->  Share Basic Information  ->  Receive / Book Slot  ->  Mentoring Conversation  ->  Agreed Action  ->  7-Day Follow-up  ->  Feedback / Next Step / Referral

The first technical setup only needs to make this journey simple, professional and reliable.

# 7. What Should NOT Be Built Before 31 December

| Do Not Build Yet | Reason |
| --- | --- |
| Mobile app | No validated need yet |
| Custom CRM | Existing tools should be sufficient initially |
| Complex website | Not necessary to test mentoring value |
| Large student database | Initial volume does not justify it |
| Automated recommendation engine | Mentoring should remain human-led |
| Large payment infrastructure | Simple payment mechanism is enough |
| Complex analytics | Basic dashboard is sufficient |
| Multiple programme packages | Let student behaviour reveal the need |
| Institutional portal | Outside the present validation objective |

If actual usage demonstrates that any of the above is necessary, it can be reconsidered jointly.

# 8. Validation Dashboard

| Measure | Why We Track It |
| --- | --- |
| Enquiries | Initial interest |
| First conversations | Actual participation |
| Repeat conversations | Continuing perceived value |
| 7-Day Actions agreed | Movement towards action |
| Actions completed | Behavioural follow-through |
| Referrals | Advocacy |
| New-to-Deepak participants | Value beyond existing relationships |
| Parent interactions | Potential stakeholder demand |
| Paid participants | Willingness to pay |
| Revenue | Early commercial evidence |

Also review qualitatively: Top recurring student needs | Key learnings | What changed? | What should change next?

# 9. Daily & Weekly Discipline for Deepak

Daily question: "What one action today will put Second Innings in contact with a real young person?"

At the end of each working day, maintain a short Founder Learning Log:

Today I spoke to...

I learned...

Something that surprised me...

Something I should change...

Tomorrow's most important action...

Every Friday: Review student themes, actions, follow-ups and learning. Avoid changing the system merely because a new idea sounds attractive.

# 10. Five Non-Negotiables

No app at this stage.

No expensive technology.

No new large manual or system unless actual usage creates the need.

Every meaningful mentoring conversation should end with an action / follow-up wherever appropriate.

Every week must include real young people - not only planning for young people.

# 11. Required Outputs from the First Working Meeting

Agree on the 90-day execution calendar.

Freeze Must Have Now / Can Wait / Not Needed.

Allocate the 1-7 October setup tasks.

Agree what Aman will teach Deepak to operate independently.

Fix the next review point before ending the meeting.

# 12. Periodic Review Meetings

To keep Aman connected with the progress and evolution of Second Innings, periodic review and update meetings will be scheduled mutually, keeping his academic calendar, examinations, assignments and other commitments in mind.

These meetings will be used to review actual student usage, discuss emerging requirements, assess what technology is or is not needed, and jointly decide the next stage of technical development.

Aman's involvement will therefore remain flexible and milestone-based. Academic commitments will always take precedence, while the association with Second Innings can continue to evolve meaningfully over the longer term.

# 13. Guiding Principle

Do not spend the next three months proving that Second Innings is a good idea. Spend them discovering whether it is genuinely useful.

Technology should support real mentoring behaviour. Real usage should tell us what technology Second Innings deserves.